## Combined MD & TD new
WORK PLAN OF CWC FOR THE F.Y. 2015-16 |  |  |  |  | Financial Progress of FF Plan Scheme for the month June, 2015
2711 FLOOD CONTROL & DRAINAGE ( PLAN)
[6 empty] | NTBO | [7 empty] | Gandhinagar
S.No | Activity | Financial Progress (INR in Crore) | Monthly Finacial targets and achievements 2015-16. | [15 empty] | Cummulative in crore | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
Mahi Division , Gandhinagar
| 2711 FLOOD CONTROL & DRAINAGE plan | Target Exp. | 0.01658 | 0.04974 | 0.20948 | 0.2758 | 0.018238 | 0.054714 | 0.10943 | 0.18238 | 0.020725 | 0.062175 | 0.18435 | 0.26725 | 0.07461 | 0.07461 | 0.12435 | 0.27357 | 0.999
|  | Actual Exp. | 0.0254 | 0.0191 | 0.0391 | 0.0836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0836
1 | 29-00-11 D.T.E.
| Traveling expenses /TTA for Officers and regular staff | Target Exp. | 0.0006 | 0.0018 | 0.0036 | 0.006 | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.00075 | 0.00225 | 0.0045 | 0.0075 | 0.0027 | 0.0027 | 0.0045 | 0.0099 | 0.03 |  |  | less expenditure as there is no pending bill of TTA/TA under this head.
|  | Actual Exp. | 0 | 0.0008 |  | 0.0008 | [12 empty] | 0.0008
2 | 29-00-13 O.E.
a | Postage Stamps for Sites, Sub Division and Division. | Target Exp. | 0.00011 | 0.00033 | 0.00066 | 0.0011 | 0.000121 | 0.000363 | 0.000726 | 0.00121 | 0.0001375 | 0.0004125 | 0.000825 | 0.001375 | 0.000495 | 0.000495 | 0.000825 | 0.001815 | 0.0055 |  |  | expenditure is nill due to to no requirement.
|  | Actual Exp. |  |  |  | 0 | [7 empty] | 0 |  |  |  | 0 | 0
b | Electricity charges for N.T.B.O.Building @ Rs.80000 /- per month | Target Exp. | 0.00192 | 0.00576 | 0.01152 | 0.0192 | 0.002112 | 0.006336 | 0.012672 | 0.02112 | 0.0024 | 0.0072 | 0.0144 | 0.024 | 0.00864 | 0.00864 | 0.0144 | 0.03168 | 0.096
|  | Actual Exp. | 0.0073 | 0.0088 | 0.0094 | 0.0255 | [12 empty] | 0.0255
c | Maintenance of office equipment | Target Exp. | 9e-05 | 0.00027 | 0.00054 | 0.0009 | 9.9e-05 | 0.000297 | 0.000594 | 0.00099 | 0.0001125 | 0.0003375 | 0.000675 | 0.001125 | 0.000405 | 0.000405 | 0.000675 | 0.001485 | 0.0045
|  | Actual Exp. |  |  | 0.0004 | 0.0004 | [12 empty] | 0.0004 |  |  | expenditure is done as per reqirement.
d | Miscellanous expenditure | Target Exp. | 4e-05 | 0.00012 | 0.00024 | 0.0004 | 4.4e-05 | 0.000132 | 0.000264 | 0.00044 | 5e-05 | 0.00015 | 0.0003 | 0.0005 | 0.00018 | 0.00018 | 0.0003 | 0.00066 | 0.002
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0
3 | 29-00-27 Minor Works (Maintenance)
a | Spectrum charges/License fees/royalty for wireless system | Target Exp. | 0.000306 | 0.000918 | 0.001836 | 0.00306 | 0.0003366 | 0.0010098 | 0.0020196 | 0.003366 | 0.0003825 | 0.0011475 | 0.002295 | 0.003825 | 0.001377 | 0.001377 | 0.002295 | 0.005049 | 0.0153 |  |  | payment qill be due in March , Dec month
|  | Actual Exp. | 0.0009 |  |  | 0.0009 | [12 empty] | 0.0009
b | AMC of computers, printers, fax, AC etc | Target Exp. | 9.6e-05 | 0.000288 | 0.000576 | 0.00096 | 0.0001056 | 0.0003168 | 0.0006336 | 0.001056 | 0.00012 | 0.00036 | 0.00072 | 0.0012 | 0.000432 | 0.000432 | 0.00072 | 0.001584 | 0.0048 |  |  | mode of payment is quaterly basis there fore 1st will be completer in June 15. and the payment will be dine on July
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
c | R&M of NTBO Elivator including AMC | Target Exp. | 0.00026 | 0.00078 | 0.00156 | 0.0026 | 0.000286 | 0.000858 | 0.001716 | 0.00286 | 0.000325 | 0.000975 | 0.00195 | 0.00325 | 0.00117 | 0.00117 | 0.00195 | 0.00429 | 0.013
|  | Actual Exp. | 0.0028 |  | 0.0028 | 0.0056 | [12 empty] | 0.0056
d | Procurement of consumable items for computers, printers, | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. | 0.0026 |  | 0.0014 | 0.004 | [12 empty] | 0.004
e | Printing & binding of year book | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 |  |  | Year books not yet finalised.
Actual Exp.
f | R&m of flood forecasting control room | Target Exp. | 0.001 | 0.003 | 0.006 | 0.01 | 0.0011 | 0.0033 | 0.0066 | 0.011 | 0.00125 | 0.00375 | 0.0075 | 0.0125 | 0.0045 | 0.0045 | 0.0075 | 0.0165 | 0.05
|  | Actual Exp. |  |  | 0.007 | 0.007 | [12 empty] | 0.007
g | Hiring of Security services for NTBO & SSD | Target Exp. | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.00165 | 0.00495 | 0.0099 | 0.0165 | 0.001875 | 0.005625 | 0.01125 | 0.01875 | 0.00675 | 0.00675 | 0.01125 | 0.02475 | 0.075
|  | Actual Exp. | 0.0064 |  | 0.005 | 0.0114 | [12 empty] | 0.0114
h | Hiring services for clenig, sweeping & maintenance of garden of NTBO complex | Target Exp. | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.00055 | 0.00165 | 0.0033 | 0.0055 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00225 | 0.00225 | 0.00375 | 0.00825 | 0.025
|  | Actual Exp. | 0.002 |  | 0.003 | 0.005 | [12 empty] | 0.005
i | Works at sites ( rnovation/upgradation) | Target Exp. | 0.0001 | 0.0003 | 0.0006 | 0.001 | 0.00011 | 0.00033 | 0.00066 | 0.0011 | 0.000125 | 0.000375 | 0.00075 | 0.00125 | 0.00045 | 0.00045 | 0.00075 | 0.00165 | 0.005
|  | Actual Exp. | 0.0005 |  | 0.004 | 0.0045 | [12 empty] | 0.0045
j | General works as upkeep/repair/renovation/upgradation/campus electrification & lighting works | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. | 0.0028 |  | 0.004 | 0.0068 | [12 empty] | 0.0068
3 | For Upgradation of 6 existing sites into telemetry system*
a | Spectrum charges/License fee for 6 nos. new telemetry sites | Target Exp. | 0.00016 | 0.00048 | 0.00096 | 0.0016 | 0.000176 | 0.000528 | 0.001056 | 0.00176 | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00072 | 0.00072 | 0.0012 | 0.00264 | 0.008 |  |  | Subject to approval of from competent authority regarding change in specification of TBRG & vatting of site specific construction drawings for BTP block with foundation, the fresh tender may be floated to carry out the said work.
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
b | Payment to survey of India for determining geographical coordinate of 6 sites for telemetry system | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. | [16 empty] | 0
c | Civil works at 6 nos site towards construction of BTP, DCU cabin & fixing arrangement for RTWLS | Target Exp. | 0.001438 | 0.004314 | 0.008628 | 0.01438 | 0.0015818 | 0.0047454 | 0.0094908 | 0.015818 | 0.0017975 | 0.0053925 | 0.010785 | 0.017975 | 0.006471 | 0.006471 | 0.010785 | 0.023727 | 0.0719
|  | Actual Exp. | [16 empty] | 0
4 | 29-00-51 Motor Vehicle
a | Procurement of new vehicle | Target Exp. | [10 empty] | 0.06 | 0.06 |  |  |  |  | 0.06 |  |  | Subject to approval of competent authority
|  | Actual Exp. | 0.0001 | 0.0095 | 0.0006 | 0.0102 | [12 empty] | 0.0102
5. A | 29-00-52 Machinery & Equipment
a | Procurement of 6 nos wireless set | Target Exp. |  |  | 0.11 | 0.11 | [12 empty] | 0.11 |  |  | new sites yet not finalised.
|  | Actual Exp. | [16 empty] | 0
b | Procurement of Computer, Printers , Computer peripherals etc, as per requirement | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. |  |  | 0.0015 | 0.0015 | [12 empty] | 0.0015
c | Procurement of Hydromet Instruments | Target Exp. | 0.0001 | 0.0003 | 0.0006 | 0.001 | 0.00011 | 0.00033 | 0.00066 | 0.0011 | 0.000125 | 0.000375 | 0.00075 | 0.00125 | 0.00045 | 0.00045 | 0.00075 | 0.00165 | 0.005
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
5. B | For Upgradation of 9 existing sites into telemetry system* | Target Exp. | 0.00736 | 0.02208 | 0.04416 | 0.0736 | 0.008096 | 0.024288 | 0.048576 | 0.08096 | 0.0092 | 0.0276 | 0.0552 | 0.092 | 0.03312 | 0.03312 | 0.0552 | 0.12144 | 0.368 |  |  | Subject to approval of from competent authority regarding change in specification of TBRG & vatting of site specific construction drawings for BTP block with foundation, the fresh tender may be floated to carry out the said work.
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
a | Supply , Installation, testing and commissioning of automatic Rainfall sensor 9 nos
b | Supply , Installation, testing and commissioning of Real time (stellite based) data communication system and data logger 9 nos .
c | Supply , Installation, testing and commissioning of Bubbler type type water level l sensor 3 nos
d | Supply , Installation, testing and commissioning of Radar type water level l sensor 6 nos .
e | Supply of Data down loading machine (lap top/ Ultrabook or equivalent) with licensed Windows 8.1 and office 2010 or latest one for each subdivision
Tapi Division, Surat
| 2711 FLOOD FORECASTING plan | Target Exp. | 0.016993 | 0.024205 | 0.047753 | 0.08785 | 0.072359 | 0.08965 | 0.11559 | 0.27771 | 0.073497 | 0.093067 | 0.062422 | 0.2291 | 0.039457 | 0.039457 | 0.062025 | 0.14094 | 0.738
|  | Actual Exp. | 0.0263 | 0.067 | 0.0022 | 0.0955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0955
1 | 29-00-11 D.T.E. | 0.0014
| Traveling expenses /TTA for Officers and regular staff | Target Exp. | 0.00588 | 0.00252 | 0.00504 | 0.0084 | 0.00088 | 0.00264 | 0.00528 | 0.0088 | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.0036 | 0.0036 | 0.006 | 0.0132 | 0.04 | 0.0004
|  | Actual Exp. | 0.0012 | 0.0002 | 0 | 0.0014 | [12 empty] | 0.0014 |  |  |  | 250
2 | 29-00-13 O.E. | 0.0037
a | Postage Stamps for Sites, Sub Division and Division. | Target Exp. | 0.00013 | 0.00039 | 0.00078 | 0.0013 | 0.000143 | 0.000429 | 0.000858 | 0.00143 | 0.0001625 | 0.0004875 | 0.000975 | 0.001625 | 0.000585 | 0.000585 | 0.000975 | 0.002145 | 0.0065
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
b | Electricity charges for Division/Sub-divisions | Target Exp. | 0.00035 | 0.00105 | 0.0021 | 0.0035 | 0.000385 | 0.001155 | 0.00231 | 0.00385 | 0.0004375 | 0.0013125 | 0.002625 | 0.004375 | 0.001575 | 0.001575 | 0.002625 | 0.005775 | 0.0175
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
c | Telephone charges for Division/Su-Divisions and maintenance of office equipment | Target Exp. | 0.00027 | 0.00081 | 0.00162 | 0.0027 | 0.000297 | 0.000891 | 0.001782 | 0.00297 | 0.0003375 | 0.0010125 | 0.002025 | 0.003375 | 0.001215 | 0.001215 | 0.002025 | 0.004455 | 0.0135
|  | Actual Exp. | 0.001 | 0.0012 | 0.0011 | 0.0033 | [12 empty] | 0.0033
d | Miscellanous expenditure | Target Exp. | 0.00013 | 0.00039 | 0.00078 | 0.0013 | 0.000143 | 0.000429 | 0.000858 | 0.00143 | 0.0001625 | 0.0004875 | 0.000975 | 0.001625 | 0.0009225 | 0.0009225 | 0.0003 | 0.002145 | 0.0065
|  | Actual Exp. | 0.0004 | 0 | 0 | 0.0004 | [12 empty] | 0.0004
|  | Sub-Total | 0.0014 | 0.0012 | 0.0011 | 0.0037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0037
3 | 29-00-27 Minor Works (Maintenance)
Recurring
a | Mantenance of Division/Sub-Divisions building . | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. | 0.0007 | 0.0005 | 0.0004 | 0.0016 | [12 empty] | 0.0016
b | R&M of site/wireless system and wireless sets / mast, batteries & other testing / measuring instruments including repair, replacement of spares and related miscellaneous works | Target Exp. | 0.00016 | 0.00048 | 0.00096 | 0.0016 | 0.00044 | 0.00132 | 0.00264 | 0.0044 | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.0018 | 0.0018 | 0.003 | 0.0066 | 0.02
|  | Actual Exp. | 0.0059 | 0.0011 | 0.0005 | 0.0075 | [12 empty] | 0.0075
c | Spectrum Charges/License fee/royalty for telemetry/wireless system | Target Exp. | 0.000464 | 0.001392 | 0.002784 | 0.00464 | 0.0005104 | 0.0015312 | 0.0030624 | 0.005104 | 0.00058 | 0.00174 | 0.00348 | 0.0058 | 0.002088 | 0.002088 | 0.00348 | 0.007656 | 0.0232
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
| Outsourcing of un-skilled assistant during mansoon, 2015 | Target Exp. | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0.06 | 0.18 | 0.06 | 0.06 |  | 0.12 |  |  |  |  | 0.3
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
d | Security services for Division Office | Target Exp. | 0.0037125 | 0.0012251 | 0.0037125 | 0.01125 | 0.0037125 | 0.0037125 | 0.0037125 | 0.01125 | 0.0037125 | 0.0037125 | 0.0037125 | 0.01125 | 0.00375 | 0.00375 | 0.00375 | 0.01125 | 0.045
|  | Actual Exp. | 0.0036 | 0.0036 | 0 | 0.0072 | [12 empty] | 0.0072
Non-Recurring
a | Repair and renovation of site office building at site Dedtalai | Target Exp. | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.00055 | 0.00165 | 0.0033 | 0.0055 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00225 | 0.00225 | 0.00375 | 0.00825 | 0.025
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
b | Repair and renovation of site office building of site Savkheda | Target Exp. | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.00055 | 0.00165 | 0.0033 | 0.0055 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00225 | 0.00225 | 0.00375 | 0.00825 | 0.025
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
c | Replacement of old batteries for wireless stations | Target Exp. | 0.000236 | 0.000708 | 0.001416 | 0.00236 | 0.0002596 | 0.0007788 | 0.0015576 | 0.002596 | 0.000295 | 0.000885 | 0.00177 | 0.00295 | 0.001062 | 0.001062 | 0.00177 | 0.003894 | 0.0118
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
f | Miscellaneous works | Target Exp. | 0.0004 | 0.0012 | 0.0024 | 0.004 | 0.00044 | 0.00132 | 0.00264 | 0.0044 | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.0018 | 0.0018 | 0.003 | 0.0066 | 0.02
|  | Actual Exp. | 0.01 | 0.006 | 0.0002 | 0.0162 | [12 empty] | 0.0162
|  | Sub total:- | 0.0202 | 0.0112 | 0.0011 | 0.0325 | [12 empty] | 0.065
4 | 29-00-51 Motor Vehicle | Target Exp. | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.0054 | 0.0054 | 0.009 | 0.0198 | 0.06
i) | Provision for POL expenses for inspection of sites & repair/maintenance of vehicles | Actual Exp. | 0.0035 | 0.0308 | 0 | 0.0343 | [12 empty] | 0.0343
|  | Sub-Total | 0.0035 | 0.0308 | 0 | 0.0343 | [12 empty] | 0.0686
5 | 29-00-52 Machinery & Equipment
i) | Metrological & Hydrological equipments | Target Exp. | 0.0003 | 0.0009 | 0.0018 | 0.003 | 0.00033 | 0.00099 | 0.00198 | 0.0033 | 0.000375 | 0.001125 | 0.00225 | 0.00375 | 0.00135 | 0.00135 | 0.00225 | 0.00495 | 0.015
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
ii) | Computer / Printer / UPS / Scanners/Xerox machine/ peripherals etc. | Target Exp. | 0.0003 | 0.0009 | 0.0018 | 0.003 | 0.00033 | 0.00099 | 0.00198 | 0.0033 | 0.000375 | 0.001125 | 0.00225 | 0.00375 | 0.00135 | 0.00135 | 0.00225 | 0.00495 | 0.015
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
iii) | Survey equipment/Wireless Set/ spares including testing and measuring equipments, voltage stabilisers, D.C. power supply & battery chargers etc | Target Exp. | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.00055 | 0.00165 | 0.0033 | 0.0055 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00225 | 0.00225 | 0.00375 | 0.00825 | 0.025
|  | Actual Exp. | 0 | 0.0236 | 0 | 0.0236 | [12 empty] | 0.0236
iv) | Office / computer furniture / modular furnitures / EPABX System / Telephone instruments / Fire safety equipments etc. | Target Exp. | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.00055 | 0.00165 | 0.0033 | 0.0055 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00225 | 0.00225 | 0.00375 | 0.00825 | 0.025
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
v) | Aquaguard / RO System (for 10 sites) | Target Exp. | 0.00036 | 0.00108 | 0.00216 | 0.0036 | 0.000396 | 0.001188 | 0.002376 | 0.00396 | 0.00045 | 0.00135 | 0.0027 | 0.0045 | 0.00162 | 0.00162 | 0.0027 | 0.00594 | 0.018
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
vi) | Miscellaneous T&P | Target Exp. | 0.0009 | 0.00096 | 0 | 0.0032 | 0.000352 | 0.001056 | 0.002112 | 0.00352 | 0.0004 | 0.0012 | 0.0024 | 0.004 | 0.00144 | 0.00144 | 0.0024 | 0.00528 | 0.016
|  | Actual Exp. | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Sub-Total | 0 | 0.0236 | 0 | 0.0236 | [12 empty] | 0.0472