## Annexure-I(Combinedupgradation)
Annexure-I
Combined Status of Upgradation of sites under Development of Water Resources Informtion System for the Month of | [9 empty] | 2015-04-01
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization : NTBO Gandhinagar.
A | Mahi Division Gandhinagar.
Sl .No. | Site Upgraded | [5 empty] | Type of site |  |  | Instrument aquired | No of W/C persons posted at present | Remarks
| Site upgraded | Name of river | Basin | District | state | Upgraded with effect from | Earlier | Upgraded | Further upgradation required |  | SWA
No site is to be upgraded in DWRIS plan scheme.
B | Tapi Div Surat
Sl .No. | Site Upgraded | [5 empty] | Type of site |  |  | Instrument aquired | No of W/C persons posted at present | Remarks
| Site upgraded | Name of river | Basin | District | state | Upgraded with effect from | Earlier | Upgraded | Further upgradation required |  | SWA
1 | Bharuch | Narmada | Narmada | Bharuch | Gujarat | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 3 | Work completed but additional man power required
2 | Ghala | Tapi | Tapi | Surat | Gujarat | 30.01.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 1 | Work completed but additional man power required
3 | Daman | Damanganga | Damanganga | UT | D&N | 10.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
4 | Dedtalai | Tapi | Tapi | Khanwa | Madhya Pradesh | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
5 | Bhusawal | Tapi | Tapi | Jalgaon | Maharashtra | 06.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
7 | Morane | Panjara | Tapi | Dhule | Maharashtra | 17.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required

## Annex-I_Tapi
Annexure-I
Annexure-I
Status of Upgradation of sites under Development of Water Resources Information System for the Month of April 2015.
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes.
Name of Organization : Tapi Division, CWC, Surat.
Sr. No. | Site upgraded | Name of River | Basin | District | State | W.e.f. (Date) | Type of Site |  | Further upgradation required | Instrument acquired | No. of W/C staff posted at present | Remarks
[7 empty] | Earlier | Upgraded
1 | Bharuch | Narmada | Narmada | Bharuch | Gujarat | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 3 | Work completed but additional man power required
2 | Ghala | Tapi | Tapi | Surat | Gujarat | 30.01.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 1 | Work completed but additional man power required
3 | Daman | Damanganga | Damanganga | UT | D&N | 10.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
4 | Dedtalai | Tapi | Tapi | Khanwa | Madhya Pradesh | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
5 | Bhusawal | Tapi | Tapi | Jalgaon | Maharashtra | 06.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
6 | Dahigaon | Girna | Tapi | Jalgaon | Maharashtra | 11.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
7 | Morane | Panjara | Tapi | Dhule | Maharashtra | 17.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required

## Annex_I_Mahi
Annexure-I
Annexure-I
Status of Upgradation of sites under Development of Water Resources Information System for the Month of April 15
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization :NTBO Gandhinagar Mahi Division
Sr. No. | Site upgraded | Name of River | Basin | District | State | W.e.f. (Date) | Type of Site |  | Further upgradation required | Instrument acquired | No. of W/C staff posted at present | Remarks
[7 empty] | Earlier | Upgraded
No site is to be upgraded in DWRIS plan scheme.

## Annexure-II (combined)
Combined Status of Opening of new sites under Development of Water Resources Informtion System for the Month of | [8 empty] | 2015-04-01
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization : NTBO Gandhinagar.
A | Mahi Division Gandhinagar.
SN | Name of Site | Name of River | Basin | District | State | Type of Site | Date of Opening | Land Status | satatus of Equipment | Status of tender process | Status of Civil work | Remark
1 | Borwa | Mahi | Mahi | Ratlam | MP | G | Not yet Finalised | Request letter sent to state authority for allocation of suitable land nearer to site. | Auto Level , ORG & Wind Wane, Current meter, Stop watch, Digital counter, SRRG, office furniture has been procured | SO for office furniture has been placed . | Civil work to be taken up after land alocation | As data for sites 2,3 & 4 will be used for inflow forecasting reconnaissance survey for suitable location in progress. Earlier selected section not found suitable after detailed survey.So new recoinnasaicce survey has been carrioed out and selected new locations are site 1. Sohargpura on river Erav.2 khandiovari site on river Som & 3 Amarpura on river Tidi.
2 | Mewasa | Mahi | Telni River changes Erav river | Ratlam | MP | GD |  | After finalisation of the location of sites necessary communication shall be made with stae authority for allocation of land.
3 | Amarpura | Mahi | Som River | Pratapgarh | Rajasthan | G | [6 empty] | °
4 | Jaisamand | Mahi |  | Udaipur | Rajasthan | GD
5 | Una | Machundri | Machundri | Junagarh | Gujarat | GD | Temporary open on 26.7.14 | Superintending Engineer, Rajkot Irrigation Circle, Rajkot alloted a plot of land size 14mx26m =364 sqm at site Una for a period of 99 years on lease basis from the date of commencement of lease agreement . The token rent for the above plot is Rs 20/- (Rupees twenty only) per annum and lumsum deposit of Rs 500/- (Rupees five hundred only). Signining of lease agreenment has been completed on 18.02.15. payment is also made. |  |  | After processing the lease agreement necessary step to be taken up for starting the civil works | G & D site at UNA temporary opened on 26/07/2014 under Sabarmati sub Division Ahmedabad and only Gauge observation started w.e.f 26/7/14.
B | Tapi Div, Surat
Sl . No. | Name of site | Name of river | Basin | District | state | Type of site | date of opening | Land status | status of equipment | status of tender process | status of civil works | remarks
1 | Kathore | Tapi | Tapi | Surat | Gujarat | G | Temporarily opened by installing temporary gauge posts on 30.09.2014 .GTS connection , site survey and X-sections have been taken. | Irrigation department, Govt. of Gujarat alloted land on lease, land has been acquired and yearly lease payment has been made. | Instruements identified . Estimates prepared. NIQ done for autolevel, rain guage and Stevenson screen. Stevenson screen and Autolevel received. | Under process | 1. Estimate prepared for RCC Gauge posts.. Tender invited and work completed. 2.Drawing and Estimate prepared for site office building. | Staff is required after opening of site.
2 | Prakasha | Gomai | Tapi | Nandurbar | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 30.09.2014. GTS connection, site survey and X-sections have been taken. | Damarkheda Gram Panchayat is agreed to provide land for site office and application has been given. Case is under process. | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. Autolevel, stevenson screen, current meter and Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts Tender invited and work in progress . 2.Estimate for civil works under preparation. | Staff is required after opening of site.
3 | Lohara | Mun | Tapi | Akola | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 28.07.2014..GTS connection, site srvey and X-sections have been taken. | Govt land is not available .Private accomadation for site office is taken on rent from Ist Aug.2014 | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. .Autolevel, stevenson screen, current meter & Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts . Tender invited and work completed. 2.Estimate for civil works under preparation. | Staff is required after opening of site.
4 | Uchhal | Tapi | Tapi | Tapi | Gujarat | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
5 | Ver | Ver | Tapi | Tapi | Gujarat | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
6 | Sindhkheda | Buray | Tapi | Dhule | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
7 | Taloda | Manyad | Tapi | Nandurbar | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
8 | Sirpur | Arunavati | Tapi | Dhule | Maharahtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
9 | Akola | Morna | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
10 | Kurankheda | Katepurna | Tapi | Akola | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
11 | Pinakwadi | Shanur | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
12 | Vankhed | Van | Tapi | Buldhana | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
0

## Annex_II_Tapi
Status of Opening of new sites under Development of Water Resources Information System for the Month of March 2015 | [10 empty] | Annexure-II
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization : NTBO, Tapi Division, CWC, Surat
Sr. No. | Name of site | Name of River | Basin | District | State | Type of Site | Date of Opening | Land Status | Status of Equipment | Status of tender process | Status of civil work | Remark
1 | Kathore | Tapi | Tapi | Surat | Gujarat | G | Temporarily opened by installing temporary gauge posts on 30.09.2014 .GTS connection , site survey and X-sections have been taken. | Irrigation department, Govt. of Gujarat alloted land on lease, land has been acquired and yearly lease payment has been made. | Instruements identified . Estimates prepared. NIQ done for autolevel, rain guage and Stevenson screen. Stevenson screen and Autolevel received. | Under process | 1. Estimate prepared for RCC Gauge posts.. Tender invited and work completed. 2.Drawing and Estimate prepared for site office building. | Staff is required after opening of site.
2 | Prakasha | Gomai | Tapi | Nandurbar | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 30.09.2014. GTS connection, site survey and X-sections have been taken. | Damarkheda Gram Panchayat is agreed to provide land for site office and application has been given. Case is under process. | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. Autolevel, stevenson screen, current meter and Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts Tender invited and work in progress . 2.Estimate for civil works under preparation. | Staff is required after opening of site.
3 | Lohara | Mun | Tapi | Akola | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 28.07.2014..GTS connection, site srvey and X-sections have been taken. | Govt land is not available .Private accomadation for site office is taken on rent from Ist Aug.2014 | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. .Autolevel, stevenson screen, current meter & Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts . Tender invited and work completed. 2.Estimate for civil works under preparation. | Staff is required after opening of site.
4 | Uchhal | Tapi | Tapi | Tapi | Gujarat | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
5 | Ver | Ver | Tapi | Tapi | Gujarat | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
6 | Sindhkheda | Buray | Tapi | Dhule | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
7 | Taloda | Manyad | Tapi | Nandurbar | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
8 | Sirpur | Arunavati | Tapi | Dhule | Maharahtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
9 | Akola | Morna | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
10 | Kurankheda | Katepurna | Tapi | Akola | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
11 | Pinakwadi | Shanur | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
12 | Vankhed | Van | Tapi | Buldhana | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.

## Annex_II_Mahi
Status of Opening of new sites under Development of Water Resources Information System for the Month of April 15 | [10 empty] | Annexure-II
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization :NTBO Gandhinagar Mahi DIivision
Sr. No. | Name of site | Basin | Name of River | District | State | Type of Site | Date of Opening | Land Status | Status of Equipment | Status of tender process | Status of civil work | Remark
1 | Borwa | Mahi | Mahi | Ratlam | MP | G | Not yet Finalised | Request letter sent to state authority for allocation of suitable land nearer to site. | Auto Level , ORG & Wind Wane, Current meter, Stop watch, Digital counter, SRRG, office furniture has been procured | SO for office furniture has been placed . | Civil work to be taken up after land alocation | As data for sites 2,3 & 4 will be used for inflow forecasting reconnaissance survey for suitable location in progress. Earlier selected section not found suitable after detailed survey.So new recoinnasaicce survey has been carrioed out and selected new locations are site 1. Sohargpura on river Erav.2 khandiovari site on river Som & 3 Amarpura on river Tidi.
2 | Mewasa | Mahi | Telni River changes Erav river | Ratlam | MP | GD |  | After finalisation of the location of sites necessary communication shall be made with stae authority for allocation of land.
3 | Amarpura | Mahi | Som River | Pratapgarh | Rajasthan | G
4 | Jaisamand | Mahi | Gomti change to Tidi River | Udaipur | Rajasthan | GD
5 | Una | Machundri | Machundri | Junagarh | Gujarat | GD | Temporary open on 26.7.14 | Superintending Engineer, Rajkot Irrigation Circle, Rajkot alloted a plot of land size 14mx26m =364 sqm at site Una for a period of 99 years on lease basis from the date of commencement of lease agreement . The token rent for the above plot is Rs 20/- (Rupees twenty only) per annum and lumsum deposit of Rs 500/- (Rupees five hundred only). Signining of lease agreenment has been completed on 18.02.15. payment is also made. |  |  | After processing the lease agreement necessary step to be taken up for starting the civil works | G & D site at UNA temporary opened on 26/07/2014 under Sabarmati sub Division Ahmedabad and only Gauge observation started w.e.f 26/7/14.
Executive Engineer

## combined-partA
WORK PLAN OF CWC FOR THE F.Y. 2014-15
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under CWC in F.Y 2014-15
For the Month of March 15 | For Month of April 2015 |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [13 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Finanacial Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach.
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | 0.12748 | 0.1316 | 0.21314 | 0.47223 | 0.0797 | 0.13777 | 0.22757 | 0.44504 | 0.081412 | 0.1428 | 0.23574 | 0.45995 | 0.14821 | 0.15381 | 0.34957 | 0.47089 | 1.8462
|  | Actual Exp. | 0.2628 | 0.0449 | 0.0662 | 0.3628 | 0.0706 | 0.108 | 0.0839 | 0.2625 | 0.106 | 0.0804 | 0.073 | 0.2594 | 0.0602 | 0.109 | 0.2108 | 0.38 | 1.272
A. | Regular Establishment | Target Exp. | 0.02792 | 0.03376 | 0.05752 | 0.1192 | 0.018712 | 0.036136 | 0.062272 | 0.11712 | 0.0199 | 0.0397 | 0.0694 | 0.129 | 0.04564 | 0.04564 | 0.0594 | 0.15068 | 0.516 | 6 | #VALUE!
|  | Actual Exp. | 0.0563 | 0.0269 | 0.0272 | 0.1104 | 0.0178 | 0.018 | 0.0313 | 0.0671 | 0.0269 | 0.0242 | 0.0279 | 0.079 | 0.0245 | 0.0223 | 0.0212 | 0.068 | 0.3245 | 0
B. | Work Charged Establishment | Target Exp. | 0.078203 | 0.051277 | 0.065887 | 0.19537 | 0.042024 | 0.052738 | 0.068809 | 0.16357 | 0.042754 | 0.054929 | 0.073192 | 0.17087 | 0.058582 | 0.058582 | 0.036525 | 0.15369 | 0.6835 | 20
|  | Actual Exp. | 0.1002 | 0.0131 | 0.0131 | 0.1264 | 0.0136 | 0.0143 | 0.0147 | 0.0426 | 0.0167 | 0.0136 | 0.032 | 0.0623 | 0.0136 | 0.0145 | 0 | 0.0281 | 0.2594 | 0
C. | Minor Works |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
a) | Construction of Site office including land cost for site | Target Exp. | 0.00495 | 0.01485 | 0.0297 | 0.0495 | 0.00495 | 0.01485 | 0.0297 | 0.0495 | 0.00375 | 0.01125 | 0.0225 | 0.0375 | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.15 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of land
ii) | Proposal for Purchase of land/Acquisition of land
iii) | Preparation of Building Plan
iv) | Preparation of Tender Documents
v) | Floating of Tender
vi) | Evaluation of Tender
vii) | Award of Work
viii) | Execution/Completion of Work
ix) | Hiring of land/building on rental basis
b) | Upgradation of existing Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents for
Cableway set
Bridge outfit
Bank operated ADCP
Gauge post
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
c) | R&M of existing Sites | Target Exp. | 0.003662 | 0.010986 | 0.021972 | 0.03662 | 0.0040282 | 0.012085 | 0.024169 | 0.040282 | 0.0045775 | 0.013732 | 0.027465 | 0.045775 | 0.016479 | 0.016479 | 0.027465 | 0.060423 | 0.1831 | 37 | 0
|  | Actual Exp. | 0.0862 | 0.0009 | 0.0052 | 0.0923 | 0.0168 | 0.0055 | 0.0057 | 0.028 | 0.0339 | 0.0226 | 0.0061 | 0.0626 | 0.0134 | 0.0514 | 0.0008 | 0.0656 | 0.2485 | 0 | 0
d) | AMC of the equipment computer, printer & photocopier etc. | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 | 0 | 0
|  | Actual Exp. | 0.002 | 0.0005 | 0.0005 | 0.003 | 0.0161 | 0.001 | 0.0005 | 0.0176 | 0.0005 | 0.0005 | 0.0006 | 0.0016 | 0.0006 | 0.0005 | 0 | 0.0011 | 0.0233 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
e) | R&M of Data Centre | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Actual Exp. | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.001 | 0.003 | 0.006 | 0.01 | 0.0004 | 0.0012 | 0.0024 | 0.004 | 0.04 | 0 | 0
f) | Out sourcing of DEO, MTS and Watch & Ward services | Target Exp. | 0.000864 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | 2 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0024 | 0.0024 | 0.0024 | 0.0072 | 0.0024 | 0.0022 | 0 | 0.0046 | 0.0118 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
g) | Snow Hydrology and Glacial Studies | Target Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Actual Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Civil works
i) | Preparation of specification for setting of Modeling Centre
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Placing o f work Order/Supply Order
Technical work
i) | Carrying out the study
h) | Hiring of Inspection Vehicles | Target Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Actual Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
D. | Motor Vehicle | Target Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Actual Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
i) | R&M of Motor Vehicle including salary of MV Driver |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | Procurement of Inspection Vehicle |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E. | Machinery & Equipment |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Actual Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Actual Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## combined-A-new
WORK PLAN OF CWC FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under CWC in F.Y 2015-16
For the Month of April 15 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [11 empty] | Amount in Crore
A | Mahi Division
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | 0.099603 | 0.065477 | 0.084287 | 0.24937 | 0.052937 | 0.065477 | 0.084287 | 0.2027 | 0.051417 | 0.060917 | 0.075167 | 0.1875 | 0.048567 | 0.052367 | 0.0114 | 0.11233 | 0.75
|  | Actual Exp. | 0.0836 | 0 | 0 | 0.0836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0836
A. | Regular Establishment | Target Exp. | 0.02 | 0.01 | 0.01 | 0.04 | 0.01 | 0.01 | 0.01 | 0.03 | 0.01 | 0.01 | 0.01 | 0.03 | 0.01 | 0.01 | 0 | 0.02 | 0.12 | 1 | Continuous work | 1 no Junior Engineer
|  | Actual Exp. | 0.0007 | 0 | 0 | 0.0007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0007
B. | Work Charged Establishment | Target Exp. | 0.073333 | 0.036667 | 0.036667 | 0.14667 | 0.036667 | 0.036667 | 0.036667 | 0.11 | 0.036667 | 0.036667 | 0.036667 | 0.11 | 0.036667 | 0.036667 | 0 | 0.073333 | 0.44 | 13 |  | Estt. of 13 WC Staff
|  | Actual Exp. | 0.0718 | 0 | 0 | 0.0718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0718
C. | Minor Works | Target Exp. | 0.00495 | 0.01485 | 0.0297 | 0.0495 | 0.00495 | 0.01485 | 0.0297 | 0.0495 | 0.00375 | 0.01125 | 0.0225 | 0.0375 | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.15 |  |  | 0 Nos. to be completed on or before 31.03.2015
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | Printing & binding of data forms & registers & year book | Actual Exp.
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
b | R&M of Regional Data center (Partition works, reparing of printer UPS, Ploter, etc) | Actual Exp.
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
C | Construction & fixing of gauge posts, target posts etc. | Actual Exp.
i | Execution of work
iv | R&M of sites/ offices including renovation, colour washing etc | Actual Exp.
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
v | Procurement of cosumable items for computers/ photocopier/Fax etc. | Actual Exp. | 0.0038 | 0 | 0 | 0.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Miscellaneous and unforeseen works | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. | Motor Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0.0073 | 0 | 0 | 0.0073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0073
i) | R&M of Motor Vehicle including salary of MV Driver | [19 empty] | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
i | Identification of equipment
ii | Preparation of tender document
iii | Floating of tender
iv | Evaluation of tender
v | Placing of order
vi | Completion of supply & payment
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.001 | 0.003 | 0.006 | 0.01 | 0.0004 | 0.0012 | 0.0024 | 0.004 | 0.04
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Identification of equipment
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
B | Tapi Division, Surat
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | 0.027876 | 0.066128 | 0.12886 | 0.22286 | 0.026764 | 0.072291 | 0.14328 | 0.24234 | 0.029995 | 0.081885 | 0.16057 | 0.27245 | 0.099642 | 0.10144 | 0.33817 | 0.35855 | 1.0962
|  | Actual Exp. | 0.1792 | 0.0449 | 0.0662 | 0.2903 | 0.0706 | 0.108 | 0.0839 | 0.2625 | 0.106 | 0.0804 | 0.073 | 0.2594 | 0.0602 | 0.109 | 0.2108 | 0.38 | 1.1922
A. | Regular Establishment | Target Exp. | 0.00792 | 0.02376 | 0.04752 | 0.0792 | 0.008712 | 0.026136 | 0.052272 | 0.08712 | 0.0099 | 0.0297 | 0.0594 | 0.099 | 0.03564 | 0.03564 | 0.0594 | 0.13068 | 0.396 | 5 |  | Estt. Of 5 Staff this includes OE
|  | Actual Exp. | 0.0556 | 0.0269 | 0.0272 | 0.1097 | 0.0178 | 0.018 | 0.0313 | 0.0671 | 0.0269 | 0.0242 | 0.0279 | 0.079 | 0.0245 | 0.0223 | 0.0212 | 0.068 | 0.3238
B. | Work Charged Establishment | Target Exp. | 0.00487 | 0.01461 | 0.02922 | 0.0487 | 0.005357 | 0.016071 | 0.032142 | 0.05357 | 0.0060875 | 0.018263 | 0.036525 | 0.060875 | 0.021915 | 0.021915 | 0.036525 | 0.080355 | 0.2435 | 7 |  | Estt. of 7 WC Staff
|  | Actual Exp. | 0.0284 | 0.0131 | 0.0131 | 0.0546 | 0.0136 | 0.0143 | 0.0147 | 0.0426 | 0.0167 | 0.0136 | 0.032 | 0.0623 | 0.0136 | 0.0145 | 0 | 0.0281 | 0.1876
C. | Minor Works
a) | Construction of Site office including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of land
ii) | Proposal for Purchase of land/Acquisition of land
iii) | Preparation of Building Plan
iv) | Preparation of Tender Documents
v) | Floating of Tender
vi) | Evaluation of Tender
vii) | Award of Work
viii) | Execution/Completion of Work
ix) | Hiring of land/building on rental basis
b) | Upgradation of existing Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Upgradation of 7 sites have been completed in 2013-14
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents for |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cableway set
Bridge outfit
Bank operated ADCP
Gauge post
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
c) | R&M of existing Sites | Target Exp. | 0.003662 | 0.010986 | 0.021972 | 0.03662 | 0.0040282 | 0.012085 | 0.024169 | 0.040282 | 0.0045775 | 0.013732 | 0.027465 | 0.045775 | 0.016479 | 0.016479 | 0.027465 | 0.060423 | 0.1831 | 37
|  | Actual Exp. | 0.0862 | .0009 | 0.0052 | 0.0923 | 0.0168 | 0.0055 | 0.0057 | 0.028 | 0.0339 | 0.0226 | 0.0061 | 0.0626 | 0.0134 | 0.0514 | 0.0008 | 0.0656 | 0.2485
d) | AMC of the equipment, computer, printer & photocopier etc. | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. | 0.002 | 0.0005 | 0.0005 | 0.003 | 0.0161 | 0.001 | 0.0005 | 0.0176 | 0.0005 | 0.0005 | 0.0006 | 0.0016 | 0.0006 | 0.0005 | 0 | 0.0011 | 0.0233
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
e) | R&M of Data Centre | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f) | Out sourcing of DEO, MTS and Watch & Ward services | Target Exp. | 0.000864 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | 2 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0024 | 0.0024 | 0.0024 | 0.0072 | 0.0024 | 0.0022 | 0 | 0.0046 | 0.0118
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
g) | Snow Hydrology and Glacial Studies | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works
i) | Preparation of specification for setting of Modeling Centre
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Placing o f work Order/Supply Order
Technical work
i) | Carrying out the study
h) | Hiring of Inspection Vehicles | Target Exp. | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1 |  | Estimate prepared . Tender invited
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0051 | 0.0058 | 0.0042 | 0.0151 | 0.0151
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
D. | Motor Vehicle | Target Exp. | 0.007 | 0.0035 | 0.0036 | 0.0198 | 0.0038 | 0.0034 | 0.0055 | 0.02178 | 0.0039 | 0.0036 | 0.004 | 0.02475 | 0.0057 | 0.0075 | 0.1816 | 0.03267 | 0.099 | 3
|  | Actual Exp. | 0.007 | 0.0035 | 0.0036 | 0.0141 | 0.0038 | 0.0034 | 0.0055 | 0.0127 | 0.0039 | 0.0036 | 0.004 | 0.0115 | 0.0057 | 0.0075 | 0.1816 | 0.1948 | 0.2331
i) | R&M of Motor Vehicle including salary of MV Driver |  | 0.007 | 0.0035 | 0.0036 | 0.0141 | 0.0038 | 0.0034 | 0.0055 | 0.0127 | 0.0039 | 0.0036 | 0.004 | 0.0115 | 0.0057 | 0.0075 | 0.0009 | 0.0141 | 0.0524 | 3
ii) | Procurement of Inspection Vehicle |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1807 | 0 | 0 | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Exp.
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0024 | 0.0072 | 0.0144 | 0.024 | 0.00264 | 0.00792 | 0.01584 | 0.0264 | 0.003 | 0.009 | 0.018 | 0.03 | 0.0108 | 0.0108 | 0.018 | 0.0396 | 0.12 |  |  | Procurement of current meter, digital counter, computers stevenson screen office furnitures, LCD monitor, Battery charger, GPS etc. have been procured.
|  | Actual Exp. | 0 | 0 | 0.0166 | 0.0166 | 0.0025 | 0.0658 | 0.0262 | 0.0945 | 0.0217 | 0.0135 | 0 | 0.0352 | 0.0291 | 0.0048 | 0.003 | 0.0369 | 0.1832
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## Part_A Tapi
WORK PLAN OF CWC FOR THE F.Y. 2014-15
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under CWC in F.Y 2014-15
For the Month of March 2015 | [5 empty] | Tapi Division, NTBO | [14 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | 0.027876 | 0.066128 | 0.12886 | 0.22286 | 0.026764 | 0.072291 | 0.14328 | 0.24234 | 0.029995 | 0.081885 | 0.16057 | 0.27245 | 0.099642 | 0.10144 | 0.33817 | 0.35855 | 1.0962
|  | Actual Exp. | 0.1792 | 0.0449 | 0.0662 | 0.2903 | 0.0706 | 0.108 | 0.0839 | 0.2625 | 0.106 | 0.0804 | 0.073 | 0.2594 | 0.0602 | 0.109 | 0.2108 | 0.38 | 1.1922
A. | Regular Establishment | Target Exp. | 0.00792 | 0.02376 | 0.04752 | 0.0792 | 0.008712 | 0.026136 | 0.052272 | 0.08712 | 0.0099 | 0.0297 | 0.0594 | 0.099 | 0.03564 | 0.03564 | 0.0594 | 0.13068 | 0.396 | 5 |  | Estt. Of 5 Staff this includes OE
|  | Actual Exp. | 0.0556 | 0.0269 | 0.0272 | 0.1097 | 0.0178 | 0.018 | 0.0313 | 0.0671 | 0.0269 | 0.0242 | 0.0279 | 0.079 | 0.0245 | 0.0223 | 0.0212 | 0.068 | 0.3238
B. | Work Charged Establishment | Target Exp. | 0.00487 | 0.01461 | 0.02922 | 0.0487 | 0.005357 | 0.016071 | 0.032142 | 0.05357 | 0.0060875 | 0.018263 | 0.036525 | 0.060875 | 0.021915 | 0.021915 | 0.036525 | 0.080355 | 0.2435 | 7 |  | Estt. of 7 WC Staff
|  | Actual Exp. | 0.0284 | 0.0131 | 0.0131 | 0.0546 | 0.0136 | 0.0143 | 0.0147 | 0.0426 | 0.0167 | 0.0136 | 0.032 | 0.0623 | 0.0136 | 0.0145 | 0 | 0.0281 | 0.1876
C. | Minor Works
a) | Construction of Site office including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of land
ii) | Proposal for Purchase of land/Acquisition of land
iii) | Preparation of Building Plan
iv) | Preparation of Tender Documents
v) | Floating of Tender
vi) | Evaluation of Tender
vii) | Award of Work
viii) | Execution/Completion of Work
ix) | Hiring of land/building on rental basis
b) | Upgradation of existing Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Upgradation of 7 sites have been completed in 2013-14
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents for |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cableway set
Bridge outfit
Bank operated ADCP
Gauge post
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
c) | R&M of existing Sites | Target Exp. | 0.003662 | 0.010986 | 0.021972 | 0.03662 | 0.0040282 | 0.012085 | 0.024169 | 0.040282 | 0.0045775 | 0.013732 | 0.027465 | 0.045775 | 0.016479 | 0.016479 | 0.027465 | 0.060423 | 0.1831 | 37
|  | Actual Exp. | 0.0862 | .0009 | 0.0052 | 0.0923 | 0.0168 | 0.0055 | 0.0057 | 0.028 | 0.0339 | 0.0226 | 0.0061 | 0.0626 | 0.0134 | 0.0514 | 0.0008 | 0.0656 | 0.2485
d) | AMC of the equipment, computer, printer & photocopier etc. | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. | 0.002 | 0.0005 | 0.0005 | 0.003 | 0.0161 | 0.001 | 0.0005 | 0.0176 | 0.0005 | 0.0005 | 0.0006 | 0.0016 | 0.0006 | 0.0005 | 0 | 0.0011 | 0.0233
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
e) | R&M of Data Centre | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f) | Out sourcing of DEO, MTS and Watch & Ward services | Target Exp. | 0.000864 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | 2 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0024 | 0.0024 | 0.0024 | 0.0072 | 0.0024 | 0.0022 | 0 | 0.0046 | 0.0118
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
g) | Snow Hydrology and Glacial Studies | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works
i) | Preparation of specification for setting of Modeling Centre
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Placing o f work Order/Supply Order
Technical work
i) | Carrying out the study
h) | Hiring of Inspection Vehicles | Target Exp. | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1 |  | Estimate prepared . Tender invited
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0051 | 0.0058 | 0.0042 | 0.0151 | 0.0151
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
D. | Motor Vehicle | Target Exp. | 0.007 | 0.0035 | 0.0036 | 0.0198 | 0.0038 | 0.0034 | 0.0055 | 0.02178 | 0.0039 | 0.0036 | 0.004 | 0.02475 | 0.0057 | 0.0075 | 0.1816 | 0.03267 | 0.099 | 3
|  | Actual Exp. | 0.007 | 0.0035 | 0.0036 | 0.0141 | 0.0038 | 0.0034 | 0.0055 | 0.0127 | 0.0039 | 0.0036 | 0.004 | 0.0115 | 0.0057 | 0.0075 | 0.1816 | 0.1948 | 0.2331
i) | R&M of Motor Vehicle including salary of MV Driver |  | 0.007 | 0.0035 | 0.0036 | 0.0141 | 0.0038 | 0.0034 | 0.0055 | 0.0127 | 0.0039 | 0.0036 | 0.004 | 0.0115 | 0.0057 | 0.0075 | 0.0009 | 0.0141 | 0.0524 | 3
ii) | Procurement of Inspection Vehicle |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1807 | 0 | 0 | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Exp.
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0024 | 0.0072 | 0.0144 | 0.024 | 0.00264 | 0.00792 | 0.01584 | 0.0264 | 0.003 | 0.009 | 0.018 | 0.03 | 0.0108 | 0.0108 | 0.018 | 0.0396 | 0.12 |  |  | Procurement of current meter, digital counter, computers stevenson screen office furnitures, LCD monitor, Battery charger, GPS etc. have been procured.
|  | Actual Exp. | 0 | 0 | 0.0166 | 0.0166 | 0.0025 | 0.0658 | 0.0262 | 0.0945 | 0.0217 | 0.0135 | 0 | 0.0352 | 0.0291 | 0.0048 | 0.003 | 0.0369 | 0.1832
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## Part_A_Mahi
WORK PLAN OF CWC FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under CWC in F.Y 2015-16
For the Month of april 15 |  |  |  | Mahi Division , |  | NTBO | [8 empty] | Gandhinagar | [5 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | 0.099603 | 0.065477 | 0.084287 | 0.24937 | 0.052937 | 0.065477 | 0.084287 | 0.2027 | 0.051417 | 0.060917 | 0.075167 | 0.1875 | 0.048567 | 0.052367 | 0.0114 | 0.11233 | 0.75
|  | Actual Exp. | 0.0836 | 0 | 0 | 0.0725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0798
A. | Regular Establishment | Target Exp. | 0.02 | 0.01 | 0.01 | 0.04 | 0.01 | 0.01 | 0.01 | 0.03 | 0.01 | 0.01 | 0.01 | 0.03 | 0.01 | 0.01 | 0 | 0.02 | 0.12 | 1 | Continuous work | 1 no Junior Engineer
|  | Actual Exp. | 0.0007 |  |  | 0.0007 | [12 empty] | 0.0007
B. | Work Charged Establishment | Target Exp. | 0.073333 | 0.036667 | 0.036667 | 0.14667 | 0.036667 | 0.036667 | 0.036667 | 0.11 | 0.036667 | 0.036667 | 0.036667 | 0.11 | 0.036667 | 0.036667 | 0 | 0.073333 | 0.44 | 13 |  | Estt. of 13 WC Staff
|  | Actual Exp. | 0.0718 |  |  | 0.0718 | [12 empty] | 0.0718
C. | Minor Works | Target Exp. | 0.00495 | 0.01485 | 0.0297 | 0.0495 | 0.00495 | 0.01485 | 0.0297 | 0.0495 | 0.00375 | 0.01125 | 0.0225 | 0.0375 | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.15 |  |  | 0 Nos. to be completed on or before 31.03.2015
|  | Actual Exp. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | Printing & binding of data forms & registers & year book | Actual Exp.
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
b | R&M of Regional Data center (Partition works, reparing of printer UPS, Ploter, etc) | Actual Exp.
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
C | Construction & fixing of gauge posts, target posts etc. | Actual Exp.
i | Execution of work
iv | R&M of sites/ offices including renovation, colour washing etc | Actual Exp.
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
v | Procurement of cosumable items for computers/ photocopier/Fax etc. | Actual Exp. | 0.0038 |  |  | 0.0038
10 | Miscellaneous and unforeseen works | Actual Exp.
D. | Motor Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0.0073 | 0 | 0 | 0.0073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0073
i) | R&M of Motor Vehicle including salary of MV Driver | [19 empty] | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
i | Identification of equipment
ii | Preparation of tender document
iii | Floating of tender
iv | Evaluation of tender
v | Placing of order
vi | Completion of supply & payment
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.001 | 0.003 | 0.006 | 0.01 | 0.0004 | 0.0012 | 0.0024 | 0.004 | 0.04
|  | Actual Exp. | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Identification of equipment
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment

## combined partB
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC
For the Month of April 15 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [16 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Finanacial Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach.
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 0.023795 | 0.014802 | 0.026187 | 0.064783 | 0.033348 | 0.09321 | 0.183 | 0.30956 | 0.03322 | 0.092826 | 0.18223 | 0.30828 | 0.075847 | 0.078147 | 0.1257 | 0.27969 | 0.948 | 3 | 0
|  | Actual Exp. | 0.0972 | 0 | 0 | 0.0972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0972 | 0 | 0
A. | Regular Establishment | Target Exp. | 0.02 | 0.0034167 | 0.0034167 | 0.026833 | 0.0034167 | 0.0034167 | 0.0034167 | 0.01025 | 0.0034167 | 0.0034167 | 0.0034167 | 0.01025 | 0.0034167 | 0.0034167 | 0 | 0.0068333 | 0.041 | 0 | 0
|  | Actual Exp. | 0.0004 | 0 | 0 | 0.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0004 | 0 | 0
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. | Minor Works
a) | Construction of Site office building including land cost for site | Target Exp. | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001125 | 0.003375 | 0.00675 | 0.01125 | 0.00045 | 0.00135 | 0.0027 | 0.0045 | 0.045 | 3 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of land
ii) | Proposal for Purchase of land/Acquisition of land
iii) | Preparation of Building Plan
iv) | Preparation of Tender Documents
v) | Floating of Tender
vi) | Evaluation of Tender
vii) | Award of Work
viii) | Execution/Completion of Work
ix) | Hiring of land/building on rental basis
b) | Works for opening of New Site | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Construction and fixing of gauge post, target post, Bench Marks etc.
c) | R&M of Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d) | Hiring of Watch & Ward Service | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
D. | Motor Vehicle
i) | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii) | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0.011253 | 0.033759 | 0.067518 | 0.11253 | 0.011594 | 0.034782 | 0.069564 | 0.11594 | 0.03069 | 0.03069 | 0.05115 | 0.11253 | 0.341 | 3 | 0
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Actual Exp. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## Combined Part-b- new
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC
For the Month of April 15 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [14 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
A | Mahi Division
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 0.023795 | 0.014802 | 0.026187 | 0.064783 | 0.0072117 | 0.014802 | 0.026187 | 0.0482 | 0.0062917 | 0.012042 | 0.020667 | 0.039 | 0.0045667 | 0.0068667 | 0.0069 | 0.018333 | 0.156
|  | Actual Exp. | 0.0972 | 0 | 0 | 0.0972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0972
A. | Regular Establishment | Target Exp. | 0.02 | 0.0034167 | 0.0034167 | 0.026833 | 0.0034167 | 0.0034167 | 0.0034167 | 0.01025 | 0.0034167 | 0.0034167 | 0.0034167 | 0.01025 | 0.0034167 | 0.0034167 | 0 | 0.0068333 | 0.041 | 0
|  | Actual Exp. | 0.0004 |  |  | 0.0004 | [12 empty] | 0.0004
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. | Minor Works
| Part B: 5 New sites (2 Gauge & 3 GD site) | Target Exp. | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001125 | 0.003375 | 0.00675 | 0.01125 | 0.00045 | 0.00135 | 0.0027 | 0.0045 | 0.045 | 3 |  | Construction of site office building including land cost for sites& Construction of site office building including land cost for Snow & Met Stations
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | Construction & fixing of gauge posts, target posts, MBM
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
b | Printing & binding of year book (Flood Appraisal Report-2014)
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
C. | Procurement of cosumable items for computers/ photocopier/Fax etc.
i | Identification of items
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
d | R& M of site office
D. | Motor Vehicle
i) | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii) | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. | Machinery & Equipment
a | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Identification of equipment
ii | Preparation of tender document
iii | Floating of tender
iv | Evaluation of tender
v | Placing of order
vi | Completion of supply & payment
b | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.00231 | 0.00693 | 0.01386 | 0.0231 | 0.00231 | 0.00693 | 0.01386 | 0.0231 | 0.00175 | 0.00525 | 0.0105 | 0.0175 | 0.0007 | 0.0021 | 0.0042 | 0.007 | 0.07
|  | Actual Exp. | 0.0968 |  |  | 0.0968 | [12 empty] | 0.0968 |  |  | Paid out standing bills of FY. 2014-15
i | Identification of equipment
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
B | Tapi Division
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 0 | 0 | 0 | 0 | 0.045705 | 0.13711 | 0.27423 | 0.45705 | 0.04709 | 0.14127 | 0.28254 | 0.4709 | 0.12465 | 0.12465 | 0.20775 | 0.45705 | 1.385 |  |  | 7NO GD and 2 Gauge site is proposed in FY 2015-16
|  | Actual Exp. | 0.0177
A. | Regular Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
|  | Actual Exp. | 0
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
|  | Actual Exp. | 0
C. | Minor Works
a) | Construction of Site office building including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0.026136 | 0.078408 | 0.15682 | 0.26136 | 0.026928 | 0.080784 | 0.16157 | 0.26928 | 0.07128 | 0.07128 | 0.1188 | 0.26136 | 0.792 | 3 | 0 | Construction of site office building including land cost for sites& Construction of site office building including land cost for Snow & Met Stations
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of land | [20 empty] | Land on lease for site Kathore finalised
ii) | Proposal for Purchase of land/Acquisition of land | [20 empty] | Land on lease for site Kathore finalised
iii) | Preparation of Building Plan | [20 empty] | Drawing estimate for Kathore completed
iv) | Preparation of Tender Documents
v) | Floating of Tender
vi) | Evaluation of Tender
vii) | Award of Work
viii) | Execution/Completion of Work
ix) | Hiring of land/building on rental basis
b) | Works for opening of New Site | Target Exp. | 0 | 0 | 0 | 0 | 0.002376 | 0.007128 | 0.014256 | 0.02376 | 0.002448 | 0.007344 | 0.014688 | 0.02448 | 0.00648 | 0.00648 | 0.0108 | 0.02376 | 0.072 | 3 | 0 | Construction & fixing of gauge posts, Target Posts and construction of D-Type and Musto Type Bench Marks & Miscellaneous and unforeseen works
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Construction and fixing of gauge post, target post, Bench Marks etc.
c) | R&M of Sites | Target Exp. | 0 | 0 | 0 | 0 | 0.001188 | 0.003564 | 0.007128 | 0.01188 | 0.001224 | 0.003672 | 0.007344 | 0.01224 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | 3 | 0
|  | Actual Exp. | 0.0011
d) | Hiring of Watch & Ward Service | Target Exp. | 0 | 0 | 0 | 0 | 0.004752 | 0.014256 | 0.028512 | 0.04752 | 0.004896 | 0.014688 | 0.029376 | 0.04896 | 0.01296 | 0.01296 | 0.0216 | 0.04752 | 0.144 | 3 | 0
|  | Actual Exp. | 0.0166 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0124 | 0.01 | 0 | 0.0224 | 0.0224
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
D. | Motor Vehicle
i) | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0
ii) | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
|  | Actual Exp. | 0
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0.011253 | 0.033759 | 0.067518 | 0.11253 | 0.011594 | 0.034782 | 0.069564 | 0.11594 | 0.03069 | 0.03069 | 0.05115 | 0.11253 | 0.341 | 3 | 0
|  | Actual Exp. | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## PartB_Tapi
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 0 | 0 | 0 | 0 | 0.045705 | 0.13711 | 0.27423 | 0.45705 | 0.04709 | 0.14127 | 0.28254 | 0.4709 | 0.12465 | 0.12465 | 0.20775 | 0.45705 | 1.385 |  |  | 7NO GD and 2 Gauge site is proposed in FY 2015-16
|  | Actual Exp. | 0.0177
A. | Regular Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
|  | Actual Exp. | 0
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
|  | Actual Exp. | 0
C. | Minor Works
a) | Construction of Site office building including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0.026136 | 0.078408 | 0.15682 | 0.26136 | 0.026928 | 0.080784 | 0.16157 | 0.26928 | 0.07128 | 0.07128 | 0.1188 | 0.26136 | 0.792 | 3 | 0 | Construction of site office building including land cost for sites& Construction of site office building including land cost for Snow & Met Stations
|  | Actual Exp. | 0
i) | Identification of land | [20 empty] | Land on lease for site Kathore finalised
ii) | Proposal for Purchase of land/Acquisition of land | [20 empty] | Land on lease for site Kathore finalised
iii) | Preparation of Building Plan | [20 empty] | Drawing estimate for Kathore completed
iv) | Preparation of Tender Documents
v) | Floating of Tender
vi) | Evaluation of Tender
vii) | Award of Work
viii) | Execution/Completion of Work
ix) | Hiring of land/building on rental basis
b) | Works for opening of New Site | Target Exp. | 0 | 0 | 0 | 0 | 0.002376 | 0.007128 | 0.014256 | 0.02376 | 0.002448 | 0.007344 | 0.014688 | 0.02448 | 0.00648 | 0.00648 | 0.0108 | 0.02376 | 0.072 | 3 | 0 | Construction & fixing of gauge posts, Target Posts and construction of D-Type and Musto Type Bench Marks & Miscellaneous and unforeseen works
|  | Actual Exp. | 0
i) | Construction and fixing of gauge post, target post, Bench Marks etc.
c) | R&M of Sites | Target Exp. | 0 | 0 | 0 | 0 | 0.001188 | 0.003564 | 0.007128 | 0.01188 | 0.001224 | 0.003672 | 0.007344 | 0.01224 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | 3 | 0
|  | Actual Exp. | 0.0011
d) | Hiring of Watch & Ward Service | Target Exp. | 0 | 0 | 0 | 0 | 0.004752 | 0.014256 | 0.028512 | 0.04752 | 0.004896 | 0.014688 | 0.029376 | 0.04896 | 0.01296 | 0.01296 | 0.0216 | 0.04752 | 0.144 | 3 | 0
|  | Actual Exp. | 0.0166 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0124 | 0.01 | 0 | 0.0224 | 0.0224
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
D. | Motor Vehicle
i) | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0
ii) | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
|  | Actual Exp. | 0
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0.011253 | 0.033759 | 0.067518 | 0.11253 | 0.011594 | 0.034782 | 0.069564 | 0.11594 | 0.03069 | 0.03069 | 0.05115 | 0.11253 | 0.341 | 3 | 0
|  | Actual Exp. | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion
iii) | Placing o f Work Order
iv) | Completion of work
g) | Snow Hydrology and Glacial Studies | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works
i) | Preparation of specification for setting of Modeling Centre
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Placing o f work Order/Supply Order
Technical work
i) | Carrying out the study
h) | Hiring of Inspection Vehicles | Target Exp. | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1
|  | Actual Exp. | 0.0086
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
D. | Motor Vehicle | Target Exp. | 0.0075 | 0 | 0 | 0.0198 | 0 | 0 | 0 | 0.02178 | 0 | 0 | 0 | 0.02475 | 0 | 0 | 0 | 0.03267 | 0.099 | 3
|  | Actual Exp. | 0.0075
i) | R&M of Motor Vehicle including salary of MV Driver |  | 0.0075 | [16 empty] | 3
ii) | Procurement of Inspection Vehicle |  | 0 | [16 empty] | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Exp.
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0024 | 0.0072 | 0.0144 | 0.024 | 0.00264 | 0.00792 | 0.01584 | 0.0264 | 0.003 | 0.009 | 0.018 | 0.03 | 0.0108 | 0.0108 | 0.018 | 0.0396 | 0.12
|  | Actual Exp. | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## Part_B_Mahi
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC
For the Month of april 15 |  |  |  | Mahi Division , |  | NTBO | [8 empty] | Gandhinagar | [5 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 0.023795 | 0.014802 | 0.026187 | 0.064783 | 0.0072117 | 0.014802 | 0.026187 | 0.0482 | 0.0062917 | 0.012042 | 0.020667 | 0.039 | 0.0045667 | 0.0068667 | 0.0069 | 0.018333 | 0.156
|  | Actual Exp. | 0.0972 | 0 | 0 | 0.0972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0972
A. | Regular Establishment | Target Exp. | 0.02 | 0.0034167 | 0.0034167 | 0.026833 | 0.0034167 | 0.0034167 | 0.0034167 | 0.01025 | 0.0034167 | 0.0034167 | 0.0034167 | 0.01025 | 0.0034167 | 0.0034167 | 0 | 0.0068333 | 0.041 | 0
|  | Actual Exp. | 0.0004 |  |  | 0.0004 | [12 empty] | 0.0004
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. | Minor Works
| Part B: 5 New sites (2 Gauge & 3 GD site) | Target Exp. | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001125 | 0.003375 | 0.00675 | 0.01125 | 0.00045 | 0.00135 | 0.0027 | 0.0045 | 0.045 | 3 |  | Construction of site office building including land cost for sites& Construction of site office building including land cost for Snow & Met Stations
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | Construction & fixing of gauge posts, target posts, MBM
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
b | Printing & binding of year book (Flood Appraisal Report-2014)
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
C. | Procurement of cosumable items for computers/ photocopier/Fax etc.
i | Identification of items
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
d | R& M of site office
D. | Motor Vehicle
i) | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii) | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. | Machinery & Equipment
a | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Identification of equipment
ii | Preparation of tender document
iii | Floating of tender
iv | Evaluation of tender
v | Placing of order
vi | Completion of supply & payment
b | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.00231 | 0.00693 | 0.01386 | 0.0231 | 0.00231 | 0.00693 | 0.01386 | 0.0231 | 0.00175 | 0.00525 | 0.0105 | 0.0175 | 0.0007 | 0.0021 | 0.0042 | 0.007 | 0.07
|  | Actual Exp. | 0.0968 |  |  | 0.0968 | [12 empty] | 0.0968 |  |  | Paid out standing bills of FY. 2014-15
i | Identification of equipment
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment

## combined part C
WORK PLAN OF MOWR FOR THE F.Y. 2014-15
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC
For the Month of April 15 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [16 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Financial Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks Tapi division Surat | Remarks Mahi division Gandhinagar
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Exp. | 0.007289 | 0.021867 | 0.043734 | 0.07289 | 0.0078694 | 0.023608 | 0.047216 | 0.078694 | 0.00838 | 0.02514 | 0.05028 | 0.0838 | 0.026568 | 0.027468 | 0.04623 | 0.10027 | 0.3352 | 0 | 0
|  | Actual Exp. | 0.0161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. | Regular Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. | Work Charged Establishment | Target Exp. | 0.00072 | 0.00216 | 0.00432 | 0.0072 | 0.000792 | 0.002376 | 0.004752 | 0.00792 | 0.0009 | 0.0027 | 0.0054 | 0.009 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | 1 | 0 | Estt. Of 1 W/C Staff | 0
|  | Actual Exp. | 0.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. | Outsourcing of JRF | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. | Minor Works
a) | Procurement of Consumabales | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 | LS | LS | Chemical (Imported & Indian) for Analysis of Chemical & Biological parameters ,Chemical and Reference solutions for Ion Meter/ AAS/GC, Gases, Solvent, Electrode for Ion Meter - 2 per lab, Electrode for Auto titrator ,Electrode for Conductivity meter, pH meter, DO meter, Glass Wares, General / Computer stationary, Batteries for UPS | Chemical (Imported & Indian) for Analysis of Chemical & Biological parameters ,Chemical and Reference solutions for Ion Meter/ AAS/GC, Gases, Solvent, Electrode for Ion Meter - 2 per lab, Electrode for Auto titrator ,Electrode for Conductivity meter, pH meter, DO meter, Glass Wares, General / Computer stationary, Batteries for UPS
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Quantification of requirement
ii) | Placing of Order
b) | AMC of Lab Equipment | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 | 0 | 0 | AMC for Indigenous/Imported Equipments, AMC, Repair of Computers / Photocopy machine etc | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
c) | Renovation of Laboratory | Target Exp. | 0.0014 | 0.0042 | 0.0084 | 0.014 | 0.00154 | 0.00462 | 0.00924 | 0.0154 | 0.00175 | 0.00525 | 0.0105 | 0.0175 | 0.0063 | 0.0063 | 0.0105 | 0.0231 | 0.07 | 2 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of Space required
ii) | Preparation of Tender Documents for renovation work
iii) | Floating of Tender
iv) | Placing o f Work Order
d) | R&M of Water Qulaity Sites | Target Exp. | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.000726 | 0.002178 | 0.004356 | 0.00726 | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.00297 | 0.00297 | 0.00495 | 0.01089 | 0.033 | 11 | 11 | 0 | 0
|  | Actual Exp. | 0.00706 | 0.00198 | 0.00396 | 0.0066 | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.02 | 0 | 0 | 0 | Misc. Lab Equipment
e) | Outsourcing of Vehicle | Target Exp. | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1 | 1 | 0 | 0
|  | Actual Exp. | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
f) | Out sourcing of DEO, MTS services | Target Exp. | 0.001824 | 0.005472 | 0.010944 | 0.01824 | 0.0020064 | 0.0060192 | 0.012038 | 0.020064 | 0.00228 | 0.00684 | 0.01368 | 0.0228 | 0.008208 | 0.008208 | 0.01368 | 0.030096 | 0.0912 | 4 | 0 | 0 | 2 No DEO req
|  | Actual Exp. | 0.0019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ICP-MS-00, AAS-0, GCMS-00, TOC-0, Auto Titrator-01, USVIS-0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.002738 | 0.008214 | 0.016428 | 0.02738 | 0.0030118 | 0.0090354 | 0.018071 | 0.030118 | 0.0034225 | 0.010268 | 0.020535 | 0.034225 | 0.012321 | 0.012321 | 0.020535 | 0.045177 | 0.1369 | 0 | 0 | Misc. Lab Equipment such as UV Spectyrophometer, Electric Oven, Siltometer, Auto pipet, Digital Burate, DO meter, oven etc. Estimates are under preperation. | Misc. Lab Equipment
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0.000473 | 0.001419 | 0.002838 | 0.00473 | 0.00215 | 0.0123 | 0.0092 | 0.0215 | 0 | 0.0059 | 0 | 0 | 0.0215 | 0 | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## Cmbnd-C-new
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC
For the Month of April 15 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [12 empty] | Amount in Crores
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
A | Mahi Division, Gnadinagar
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Expenditure | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001125 | 0.003375 | 0.00675 | 0.01125 | 0.00045 | 0.00135 | 0.0027 | 0.0045 | 0.045
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. | Regular Establishment | Target Expenditure | [17 empty] | 0 | 0
Actual Expenditure
B. | Work Charged Establishment | Target Expenditure | [17 empty] | 0 | 0
Actual Expenditure
C. | Outsourcing of JRF | Target Expenditure | [17 empty] | 0 | 0
Actual Expenditure
D. | Minor Works | Target Expenditure | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.025 | LS | LS | Chemical (Imported & Indian) for Analysis of Chemical & Biological parameters ,Chemical and Reference solutions for Ion Meter/ AAS/GC, Gases, Solvent, Electrode for Ion Meter - 2 per lab, Electrode for Auto titrator ,Electrode for Conductivity meter, pH meter, DO meter, Glass Wares, General / Computer stationary, Batteries for UPS
Actual Expenditure
1 | Hiring services for Data entry services & MTS for Water Quality lab | [20 empty] | Continued work
3 | Rnovation of water quality lab | [20 empty] | Partion work for micro biology room, & man Lab , Fixing of drawer & tray
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
4 | Procurement of chemical ( imported & Indian) for anlysis of chemial & biological parameter
i | Identification of chemicals & equipment etc
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
6 | Renovation of Lab at sites | [20 empty] | continued work
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Expenditure
Actual Expenditure
b) | Purchase of Low value equipment (< 5 Lakh) | Target Expenditure | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.02 |  |  | Misc. Lab Equipment
Actual Expenditure
i | Identification of equipment
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
f) | Out sourcing of DEO, MTS services | Target Expenditure | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 2 | 2 | 2 No DEO req
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ICP-MS-00, AAS-0, GCMS-00, TOC-0, Auto Titrator-01, USVIS-0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Expenditure | 0.001538 | 0.004614 | 0.009228 | 0.01538 | 0.0016918 | 0.0050754 | 0.010151 | 0.016918 | 0.0019225 | 0.0057675 | 0.011535 | 0.019225 | 0.006921 | 0.006921 | 0.011535 | 0.025377 | 0.0769 |  |  | Misc. Lab Equipment
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0.000473 | 0.001419 | 0.002838 | 0.00473 | 0.00215 | 0.0123 | 0.0092 | 0.0215 | 0 | 0.0059 |  |  | 0.0215
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion
B | Tapi Division, Gnadinagar
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Expenditure | 0.005804 | 0.017412 | 0.034824 | 0.05804 | 0.0063844 | 0.019153 | 0.038306 | 0.063844 | 0.007255 | 0.021765 | 0.04353 | 0.07255 | 0.026118 | 0.026118 | 0.04353 | 0.095766 | 0.2902
|  | Actual Expenditure | 0.0161
A. | Regular Establishment | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0
B. | Work Charged Establishment | Target Expenditure | 0.00072 | 0.00216 | 0.00432 | 0.0072 | 0.000792 | 0.002376 | 0.004752 | 0.00792 | 0.0009 | 0.0027 | 0.0054 | 0.009 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | 1 |  | Estt. Of 1 W/C Staff
|  | Actual Expenditure | 0.0028
C. | Outsourcing of JRF | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure
D. | Minor Works
a) | Procurement of Consumabales | Target Expenditure | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 | LS |  | Chemical (Imported & Indian) for Analysis of Chemical & Biological parameters ,Chemical and Reference solutions for Ion Meter/ AAS/GC, Gases, Solvent, Electrode for Ion Meter - 2 per lab, Electrode for Auto titrator ,Electrode for Conductivity meter, pH meter, DO meter, Glass Wares, General / Computer stationary, Batteries for UPS
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Quantification of requirement
ii) | Placing of Order
b) | AMC of Lab Equipment | Target Expenditure | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 |  |  | AMC for Indigenous/Imported Equipments, AMC, Repair of Computers / Photocopy machine etc
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
c) | Renovation of Laboratory | Target Expenditure | 0.001 | 0.003 | 0.006 | 0.01 | 0.0011 | 0.0033 | 0.0066 | 0.011 | 0.00125 | 0.00375 | 0.0075 | 0.0125 | 0.0045 | 0.0045 | 0.0075 | 0.0165 | 0.05 | 1
|  | Actual Expenditure | 0
i) | Identification of Space required
ii) | Preparation of Tender Documents for renovation work
iii) | Floating of Tender
iv) | Placing o f Work Order
d) | R&M of Water Qulaity Sites | Target Expenditure | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.000726 | 0.002178 | 0.004356 | 0.00726 | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.00297 | 0.00297 | 0.00495 | 0.01089 | 0.033 | 11 | 11
|  | Actual Expenditure | 0.0064
e) | Outsourcing of Vehicle | Target Expenditure | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1 | 1
|  | Actual Expenditure | 0.005
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
f) | Out sourcing of DEO, MTS services | Target Expenditure | 0.000864 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | 2
|  | Actual Expenditure | 0.0019
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Expenditure | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.0054 | 0.0054 | 0.009 | 0.0198 | 0.06 |  |  | Misc. Lab Equipment such as UV Spectyrophometer, Electric Oven, Siltometer, Auto pipet, Digital Burate, DO meter, oven etc. Estimates are under preperation.
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
D. | Motor Vehicle | Target Exp. | 0.0075 | 0 | 0 | 0.0198 | 0 | 0 | 0 | 0.02178 | 0 | 0 | 0 | 0.02475 | 0 | 0 | 0 | 0.03267 | 0.099 | 3
|  | Actual Exp. | 0.0075
i) | R&M of Motor Vehicle including salary of MV Driver |  | 0.0075 | [16 empty] | 3
ii) | Procurement of Inspection Vehicle |  | 0 | [16 empty] | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Exp.
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0024 | 0.0072 | 0.0144 | 0.024 | 0.00264 | 0.00792 | 0.01584 | 0.0264 | 0.003 | 0.009 | 0.018 | 0.03 | 0.0108 | 0.0108 | 0.018 | 0.0396 | 0.12
|  | Actual Exp. | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## Part_C_Tapi
WORK PLAN OF MOWR FOR THE F.Y. 2014-15
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC
For the Month of March 2015 | [5 empty] | Tapi Division, NTBO | [14 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Expenditure | 0.005804 | 0.017412 | 0.034824 | 0.05804 | 0.0063844 | 0.019153 | 0.038306 | 0.063844 | 0.007255 | 0.021765 | 0.04353 | 0.07255 | 0.026118 | 0.026118 | 0.04353 | 0.095766 | 0.2902
|  | Actual Expenditure | 0.0161
A. | Regular Establishment | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0
B. | Work Charged Establishment | Target Expenditure | 0.00072 | 0.00216 | 0.00432 | 0.0072 | 0.000792 | 0.002376 | 0.004752 | 0.00792 | 0.0009 | 0.0027 | 0.0054 | 0.009 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | 1 |  | Estt. Of 1 W/C Staff
|  | Actual Expenditure | 0.0028
C. | Outsourcing of JRF | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure
D. | Minor Works
a) | Procurement of Consumabales | Target Expenditure | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 | LS |  | Chemical (Imported & Indian) for Analysis of Chemical & Biological parameters ,Chemical and Reference solutions for Ion Meter/ AAS/GC, Gases, Solvent, Electrode for Ion Meter - 2 per lab, Electrode for Auto titrator ,Electrode for Conductivity meter, pH meter, DO meter, Glass Wares, General / Computer stationary, Batteries for UPS
|  | Actual Expenditure | 0
i) | Quantification of requirement
ii) | Placing of Order
b) | AMC of Lab Equipment | Target Expenditure | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 |  |  | AMC for Indigenous/Imported Equipments, AMC, Repair of Computers / Photocopy machine etc
|  | Actual Expenditure | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
c) | Renovation of Laboratory | Target Expenditure | 0.001 | 0.003 | 0.006 | 0.01 | 0.0011 | 0.0033 | 0.0066 | 0.011 | 0.00125 | 0.00375 | 0.0075 | 0.0125 | 0.0045 | 0.0045 | 0.0075 | 0.0165 | 0.05 | 1
|  | Actual Expenditure | 0
i) | Identification of Space required
ii) | Preparation of Tender Documents for renovation work
iii) | Floating of Tender
iv) | Placing o f Work Order
d) | R&M of Water Qulaity Sites | Target Expenditure | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.000726 | 0.002178 | 0.004356 | 0.00726 | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.00297 | 0.00297 | 0.00495 | 0.01089 | 0.033 | 11 | 11
|  | Actual Expenditure | 0.0064
e) | Outsourcing of Vehicle | Target Expenditure | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1 | 1
|  | Actual Expenditure | 0.005
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
f) | Out sourcing of DEO, MTS services | Target Expenditure | 0.000864 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | 2
|  | Actual Expenditure | 0.0019
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Expenditure | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.0054 | 0.0054 | 0.009 | 0.0198 | 0.06 |  |  | Misc. Lab Equipment such as UV Spectyrophometer, Electric Oven, Siltometer, Auto pipet, Digital Burate, DO meter, oven etc. Estimates are under preperation.
|  | Actual Expenditure | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f work Order
iv) | Completion of work
D. | Motor Vehicle | Target Exp. | 0.0075 | 0 | 0 | 0.0198 | 0 | 0 | 0 | 0.02178 | 0 | 0 | 0 | 0.02475 | 0 | 0 | 0 | 0.03267 | 0.099 | 3
|  | Actual Exp. | 0.0075
i) | R&M of Motor Vehicle including salary of MV Driver |  | 0.0075 | [16 empty] | 3
ii) | Procurement of Inspection Vehicle |  | 0 | [16 empty] | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Exp.
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0024 | 0.0072 | 0.0144 | 0.024 | 0.00264 | 0.00792 | 0.01584 | 0.0264 | 0.003 | 0.009 | 0.018 | 0.03 | 0.0108 | 0.0108 | 0.018 | 0.0396 | 0.12
|  | Actual Exp. | 0
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion

## Part_C_Mahi
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC
For the Month of april 15 |  |  |  | Mahi Division , |  | NTBO | [8 empty] | Gandhinagar | [5 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Expenditure | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.001125 | 0.003375 | 0.00675 | 0.01125 | 0.00045 | 0.00135 | 0.0027 | 0.0045 | 0.045
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. | Regular Establishment | Target Expenditure | [17 empty] | 0 | 0
Actual Expenditure
B. | Work Charged Establishment | Target Expenditure | [17 empty] | 0 | 0
Actual Expenditure
C. | Outsourcing of JRF | Target Expenditure | [17 empty] | 0 | 0
Actual Expenditure
D. | Minor Works | Target Expenditure | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.025 | LS | LS
|  | Actual Expenditure | [19 empty] | Chemical (Imported & Indian) for Analysis of Chemical & Biological parameters ,Chemical and Reference solutions for Ion Meter/ AAS/GC, Gases, Solvent, Electrode for Ion Meter - 2 per lab, Electrode for Auto titrator ,Electrode for Conductivity meter, pH meter, DO meter, Glass Wares, General / Computer stationary, Batteries for UPS
1 | Hiring services for Data entry services & MTS for Water Quality lab | [20 empty] | Continued work
3 | Rnovation of water quality lab | [20 empty] | Partion work for micro biology room, & man Lab , Fixing of drawer & tray
i | Preparation of NIQ & floating of NIQ
ii | Award of work
iii | Execution of work & payment
4 | Procurement of chemical ( imported & Indian) for anlysis of chemial & biological parameter
i | Identification of chemicals & equipment etc
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
6 | Renovation of Lab at sites | [20 empty] | continued work
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Expenditure
Actual Expenditure
b) | Purchase of Low value equipment (< 5 Lakh) | Target Expenditure | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.02 |  |  | Misc. Lab Equipment
Actual Expenditure
i | Identification of equipment
ii | Preparation of specification
iii | Calling of LPC meeting
iv | Placing of supply order
v | Completion of supply & payment
f) | Out sourcing of DEO, MTS services | Target Expenditure | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 2 | 2 | 2 No DEO req
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Preparation of Tender Documents
ii) | Floating of Tender
iii) | Placing o f Work Order
iv) | Completion of work
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ICP-MS-00, AAS-0, GCMS-00, TOC-0, Auto Titrator-01, USVIS-0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i) | Identification of Equipments
ii) | Preparation of Tender Documents
iii) | Floating of Tender
iv) | Evaluation of Tender
v) | Placing o f Supply Order
vi) | Completion of work
b) | Purchase of Low value equipment (< 5 Lakh) | Target Expenditure | 0.001538 | 0.004614 | 0.009228 | 0.01538 | 0.0016918 | 0.0050754 | 0.010151 | 0.016918 | 0.0019225 | 0.0057675 | 0.011535 | 0.019225 | 0.006921 | 0.006921 | 0.011535 | 0.025377 | 0.0769 |  |  | Misc. Lab Equipment
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0.000473 | 0.001419 | 0.002838 | 0.00473 | 0.00215 | 0.0123 | 0.0092 | 0.0215 | 0 | 0.0059 |  |  | 0.0215
i) | Identification of Equipments
ii) | Preparation of Specification
iii) | Calling of LPC meeting
iv) | Placing o f Supply Order
v) | Completion